## Burn down chart
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 48 | 48
1 |  | 30
2 |  | 2
Sprint 2 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 |  | 34
19 |  | 30
18 |  | 30
17 |  | 28
16 |  | 25
15 |  | 22
14 |  | 22
13 |  | 19
12 |  | 18
11 |  | 17
10 |  | 15
9 |  | 15
8 |  | 13
7 |  | 12
6 |  | 9
5 |  | 7
4 |  | 4
3 |  | 1
2 |  | 1
1 |  | 0
0 | 0 | 0